## Timeline
Tendering Timeline | Instructions for Procurement Co-ordinators 1. This Tendering Timeline provides an estimate of the time required for the typical activities undertaken as part of a tendering process. It should be considered and adjusted on a case by case basis with advice from the relevant Category Owner and Enterprise Procurement (as appropriate). More time may be required for particular activities depending on the complexity of the procurement project. 2. Completion of tasks set out in this timeline is the responsibility of the UQ representative responsible for undertaking the procurement process (Procurement Co-ordinator). This is typically the project manager responsible for the delivery of the overall project outcome or the manager of the relevant function undertaking the procurement. 3. Category Owners and Enterprise Procurement have a support, advisory and assurance role and Contract Delegates are responsible for approving procurement decisions. Time must be allowed for appropriate consultation, review and approval at each stage, these activities are shown in red. 4. This Tendering Timeline will need to be adjusted as your procurement activity progresses to reflect the actual completion dates of activities. * Please refer to the Procurement Policy and the Procurement Procedure for more information about roles and responsibilities
[ Procurement Name ] | [ Ref Number ]
Estimated Total Value $ [ Insert ] | Baseline | Actual | Latest Estimate | Duration in Calendar Days | Duration in Weeks | Comments
PLANNING
START | 2019-06-13 | 2019-06-13 | 2019-06-13
Consultation / Identify Stakeholders | 2019-06-20 |  | 2019-06-20 | 7 | 1
Demand Analysis / Existing Solutions / Estimated Value | 2019-06-27 |  | 2019-06-27 | 7 | 1
Market Analysis | 2019-06-30 |  | 2019-06-30 | 3 | 0.42857
Procurement Strategy (EOI, RFQ or ITO) | 2019-07-07 |  | 2019-07-07 | 7 | 1
Contract Approach | 2019-07-10 |  | 2019-07-10 | 3 | 0.42857
Review & Approval | 2019-07-17 |  | 2019-07-17 | 7 | 1
Planning Outputs - Procurement Plan; Exemption (if required) |  |  |  | 34 | 4.8571
DOCUMENTATION
Tender Scope and Requirements | 2019-07-24 |  | 2019-07-24 | 7 | 1
Tender Process and Probity Considerations | 2019-07-31 |  | 2019-07-31 | 7 | 1
Evaluation Plan | 2019-08-07 |  | 2019-08-07 | 7 | 1
Draft Contract | 2019-08-14 |  | 2019-08-14 | 7 | 1
Tender Documentation | 2019-08-21 |  | 2019-08-21 | 7 | 1
Review & Approval | 2019-08-28 |  | 2019-08-28 | 7 | 1
Documentation Outputs - EOI/RFQ/ITO; Draft Contract; Evaluation Plan; COI Declaration |  |  |  | 42 | 6
TENDER PUBLICATION |  |  |  |  | 0
Supplier Briefing | 2019-08-31 |  | 2019-08-31 | 3 | 0.42857
EOI / RFQ / ITO in market | 2019-09-28 |  | 2019-09-28 | 28 | 4
Tender Publication Outputs - Clarifications and Receipt of Offers |  |  |  | 31 | 4.4286
EVALUATION
Tender Evaluation and Clarifications | 2019-10-05 |  | 2019-10-05 | 7 | 1
Supplier Presentations / Demonstrations | 2019-10-12 |  | 2019-10-12 | 7 | 1
Moderation | 2019-10-19 |  | 2019-10-19 | 7 | 1
Supplier Selection | 2019-10-26 |  | 2019-10-26 | 7 | 1
Review & Approval | 2019-11-02 |  | 2019-11-02 | 7 | 1
Evaluation Outputs - Recommendation Report; Negotiation Plan |  |  |  | 35 | 5
NEGOTIATE & CONTRACT |  |  |  |  | 0
Negotiation Planning & Negotiate | 2019-11-16 |  | 2019-11-16 | 14 | 2
Contract Execution (contracting phase is variable in time and can take months depending on complexity and departures from standard UQ contract terms) | 2019-11-30 |  | 2019-11-30 | 14 | 2
Review & Approval & notification of Procurement Outcome | 2019-12-09 |  | 2019-12-09 | 9 | 1.2857
Negotiate and Contract Outputs - Executed Contract; Contract Record; Negotiation Report |  |  |  | 37 | 5.2857
FINISH | 2019-12-09 | 0 | 2019-12-09 | 179 | 25.5714
Formulas:
Actual = [Baseline]
Latest Estimate = [Actual]
Latest Estimate = IF([Actual]>0,[Actual],[Latest Estimate, row above]+[Duration in Calendar Days])
Baseline = [Baseline, row above]+[Duration in Calendar Days]
Baseline = B11+[Duration in Calendar Days]