## Slide 1
Clarifications
Offers
Contract
Contract Briefing Note
(if required)
Contract Record
Contract Management Plan (if required)
Procurement Recommendation Report
Negotiation Plan
(if required)
RFQ / ITO / EOI
Draft Contract
Evaluation Plan
Procurement Plan
Exemption
(if required)
Plan (3-6 Weeks)
Consultation
Document (3-5 Weeks)
Tender Scope
Evaluate (3-5 Weeks)
Tender Evaluation
Negotiate & Contract (5-7 Weeks)
Identify Stakeholders
Demand Analysis
Existing Solutions
Ongoing Operations
Market Analysis
Estimated Value
Procurement Strategy
Contract Approach
Risk Assessment
Tender Requirements
Tendering Process
Evaluation Plan
Draft Contract
Tender Documentation
Publish Tender
ITO
(4-8 Weeks)
EOI
(3-4 Weeks)
RFQ
(2-4 Weeks)
Supplier Presentations
Moderation
Supplier Selection
Negotiation
Contract Execution
Record Contract
Notification of Procurement Outcome
Estimated Tendering Process Timeline (16 – 31 weeks)
Outputs