## Instructions
Risk Assessment and Management Plan Template
Clinical Trial Risk Register Template [Version 1.5]
Objective of this template
This template has been developed as a guide to assist you in the identification of relevant risks associated with your clinical trial project and also provides potential risk mitigation actions for your consideration. You are encouraged to develop and tailor your risk assessment to make it very specific for your trial/project.
Risk assessment terminology explained
Risk Owner
A risk owner is a person or persons who has been given the authority, and is therefore accountable for managing a particular risk. In case of clinical trials this would be the CI.
Likelihood (L)
Likelihood is the chance that the risk event might happen. Likelihood is rated on a 5 point scale - refer to risk matrix.
Consequence (C)
A consequence is the impact of a risk event (if the risk is realized) on the objectives. Consequence is rated on a 5 point scale - refer to risk
matrix.
Risk Score
A consequence is the impact of a risk event (if the risk is realized) on the objectives. Consequence is rated on a 5 point scale - refer to risk
matrix.
The risk score is based on an addition of the Likelihood and Consequence scores and is grouped into four categories: Low, Moderate, High and Extreme. The ‘heat map’ (refer to risk matrix) based on the risk scores is as follows:
Managed Risk Level (MRL)
It is the level of risk taking into consideration the total effectiveness of all the existing controls or risk treatments that act upon that risk.
Target Risk Level (TRL)
It is the desired (or acceptable) level of risk considering the University’s risk appetite and tolerance levels, to be achieved via implementation of proposed controls.
Control Effectiveness
A control is any action taken by the governing body, management and other parties to increase the likelihood that risks will be managed and established objectives and goals will be achieved. Controls are assessed for their effectiveness on a 3 point scale (Low, Medium and High) and against the following elements: control objectives and scope; control documentation; awareness and understanding about the control; resources; actual operation of the control; and monitoring. The following table refers.
Low | Medium (Only if all of the following requirements are met or exceeded) | High (Only if all of the following requirements are met or exceeded)
 Lack of clarity of control objectives and scope. Limited or no documentation of control.  Limited understanding of the operation and significance of the control by those responsible for its effectiveness.  Inadequate resources (funds, people, system, time etc.) for the effective operation of the control.  No or limited evidence of the actual operation of the control or its effectiveness.  The control is not subject to ongoing monitoring or annual reviews/assessments. |  The control objectives and scope are broadly defined and appear appropriate given the underlying reason. Control is partially documented.  Key personnel have a good understanding of the operation and significance of the control.  Resources (funds, people, system, time etc.) have been allocated for the effective operation of the control, but are not always available.  There is verifiable evidence that the control is in operation most of the time, but not always.  The control is assessed annually for effectiveness and the results indicate the control is moderately achieving its objectives. |  The control is well defined with clarity of objectives and scope (both of which are aligned with the underlying reason for the control), is embedded in the relevant processes/activities, categorised as mandatory, and properly documented.  Managers and staff responsible for the effective operation of the control have a very good understanding of its operations and significance.  Adequate resources (funds, people, system, time etc.) have been allocated and are always available to ensure the effective operation of the control.  There is verifiable and compelling evidence that the control is consistently and reliably applied and is performing as expected/designed.  The control is actively monitored and is also subject to annual reviews. Monitoring and review results indicate the control is achieving its objectives.
Feedback
We very much welcome your feedback to assist us in continuously improving this template. Please email your suggestions for changes and improvements to: enterprise.risk@uq.edu.au. Thank you!

## Risk Assessment
Clinical Trial Research Risk Assessment and Management Plan | [11 empty] | Version 1.5
Research Project Name(s) | [6 empty] | Project Start Date
Research Project Objective(s) | [6 empty] | Project End Date:
Author and Contact Details: | [6 empty] | Chief Investigator (CI):
Risk Owner: | [6 empty] | Updated On: | 2021-07-08 10:13 | Version Control: | Draft | 1
Authorising Officer: | refer to Risk Action Table, Risk Matrix | < Insert Name > | Please select | P | I do not endorse the proposed contract/project/activity due to the inability to manage the risks to an acceptable level
Signature: |  | < Insert Signature > |  | P | i.e. the proposed project/contract/activity risk level does not sufficiently weigh up against the benefits it would achieve
Comments:
Categories / Areas | Potential risk exposures you need to manage Is this relevant to your study? | Risk (including threats, vulnerabilities and consequences) | Existing controls and their effectiveness |  | Managed (Current) Risk Analysis |  | Additional proposed controls to lower MRL to TRL | Due date for implementing additional controls | Person responsible for implementing additional proposed controls |  | Target (Future) Risk Analysis
|  |  | Include any existing risk mitigations already in place. | Consequences | Likelihood | MRL | Potential risk mitigations you could consider. |  |  | Consequences | Likelihood | TRL
1. Participant Consent, Rights and Confidentiality
Participant Recruitment and Consent | ° Recruitment is within protocol requirements ° Burden of study visits understood and compensated ° Population vulnerabilities understood | Serious breach of protocol or ethics committee requirements resulting in critical consequences: ° significant financial losses and lack of due diligence defence (i.e. no insurance cover for claims where CT was performed in breach of the terms of the protocol) ° reputation damage and deterioration in stakeholder relationships, confidence and future support |  |  |  | #N/A | [] Ensure trial is conducted under GCP [] Site training and visit, additional training as required [] Understanding of responsibilities by all trial staff [] Provide resources necessary for participant management/support, for example counselling [] Add other proposed controls for implementation |  |  |  |  | #N/A
Particpant Information and Consent | ° Participant Information and Consent process ° Consent is appropriate for vulnerable groups | Failure to obtain fully informed participant consent, or legal guardian's consent, resulting in critical consequences: ° legal action and significant financial losses (i.e. no insurance cover for claims where CT was performed without prior informed written consent) ° reputation damage and credibility, cessation of project |  |  |  | #N/A | [] Ensure Participant Information Sheet and Consent form are signed by the participant prior to commencement of study [] Ensure there participant is fully informed prior to agreement through verbal instruction [] Allow participant to ask questions [] Add other proposed controls for implementation |  |  |  |  | #N/A
Particpant Confidentiality | ° All participant documentation is securely managed ° Privacy is maintained ° Data is secure | Breach of confidentiality, such as: inadequate data security measures, identifiable data transferred out of Australia, resulting in significant breach of regulations and reputational damage |  |  |  | #N/A | [] Understanding of responsibilities by all trial staff [] Provide adequate resources to maintain trial documentation and security [] Incorporate adequate safeguards into the research design such as an appropriate data safety monitoring plan, and procedures to protect the confidentiality of the data (e.g. encryption, codes, and passwords) [] Add other proposed controls for implementation |  |  |  |  | #N/A
Particpant Privacy | ° Is the research question of sufficient importance to justify the intrusion? ° Is the invasion of privacy involved acceptable in light of the subjects' reasonable expectations of privacy in the situation under study? ° HREC Approval obtained for any intrusion. | Imbalance between CT objectives and the intrusion and/or privacy invasion imposed on the participants. |  |  |  | #N/A | [] Access to such records for legitimate research purposes is generally acceptable, as long as the researcher protects the confidentiality of that information [] Provide complete information in the protocol regarding the experimental design and the scientific rationale underlying the proposed research, including the results of previous animal and human studies. [] Assemble a research team with sufficient expertise and experience to conduct the research. [] Ensure that the projected sample size is sufficient to yield useful results. [] Collect data from standard-of-care procedures to avoid unnecessary risk, particularly for invasive or risky procedures (e.g., spinal taps, cardiac catheterization) [] Add other proposed controls for implementation |  |  |  |  | #N/A
| ADD other identified risks not included above | Risk of (describe risk event), due to (describe vulnerability / threats) resulting in (describe impact) | Add existing controls that may be unique to your activity |  |  | #N/A | [] Add other proposed controls for implementation |  |  |  |  | #N/A
2. Reliability of Trial Results
Reliability of Trial Results | Reliability of trial results, e.g. ° Trial is undertaken according to GCP requirements, e.g. staff are appropriately credentialed ° Statistical justification ° Process for reporting protocol deviations and violations ° Reliability of patient entered data ° Assessment outcomes understood ° Randomisation / blinding is appropriate | Risk of possible fraud in collection of data or errors in analysis of data leading to research misconduct, critical consequences to project, reputation damage and deterioration in stakeholder relationships, confidence and future support. |  |  |  | #N/A | [] Ensure trial is conducted under GCP [] Provide standard operating procedures for trial activities and ensure SOPs are implemented accordingly and updated when needed [] Ensure that all key research data is analysed by independent person(s) [] Active ongoing self-auditing best practice processes implemented as well as regular visits by an independent Data Safety and Monitoring Board member [] Ensure that the projected sample size is sufficient to yield useful results. [] Case Report Forms follow protocol requirements [] Delegation log available [] Process for reporting protocol deviations and violations [] Assessment outcomes understood [] Randomisation / blinding is appropriate [] Add other proposed controls for implementation |  |  |  |  | #N/A
3. Legal and Regulatory Compliance
Legislative Requirements | ° Commonwealth Legislation ° State Legislation ° TGA notification ° Site Requirements ° Codes (National Statement) ° Medicines Australia Clinical Trial Protection obligations if UQ is acting as Sponsor ° HREC Requirements | Risk of breaching legislative requirements due to inability to demonstrate compliance with relevant Commonwealth Legislation, State Legislation, TGA notification and Codes (National Statement) |  |  |  | #N/A | [] Identify relevant Commonwealth, Interstate, State legislation and Codes with appropriate measures in place (e.g. via SOPs) to ensure full compliance [] TGA notification submitted/lodged [] Ensure data is maintained and transferred according to required standard [] Register trial on WHO approved registry [] Review all necessary contracts and ensure full compliance with contract requirements via e.g. SOPs [] Add other proposed controls for implementation |  |  |  |  | #N/A
Insurance Declaration | Does the trial involve any of the following: ° patients aged 5 and below; ° patients who are pregnant; ° overseas sites? NB Refer Definition of "Clinical Trial" for Insurance purposes (includes human research studies) | Risk of inadequate insurance coverage due to lack of declaration of trial to insurer prior to commencement: ° involving patients aged 5 and below, or pregnancy related (unless only observational/non-invasive, data analysis or data gathering survey) ° being undertaken overseas (non-Australian trials) where local insurance cover is required |  |  |  | #N/A | [] Submit the online Insurance for Human Research Studies - Declaration for Approval prior to the commencement of the trial (PPL 4.20.03, Section 3.1.5.1): https://survey.app.uq.edu.au/clinical-trials-declaration-12102020 [] Submit an update to the online Declaration to reflect amendments to the trial [] Add other proposed controls for implementation |  |  |  |  | #N/A
Insurance Notification | Does the trial not involve any of the following: ° patients aged 5 and below; ° patients who are pregnant; ° overseas sites? NB Refer Definition of "Clinical Trial" for Insurance purposes (includes human research studies) | Risk of inadequate insurance coverage due to lack of notification of trial to insurer as part of annual insurance renewal (all trials other than those already declared prior to commencement - see above row). |  |  |  | #N/A | [] Submit the online Insurance for Human Research Studies - Notification after ethics approval (PPL 4.20.03, Section 3.1.5.1): https://survey.app.uq.edu.au/clinical-trials-data [] Submit an update to the online Notification to reflect amendments to the trial
No Insurance Coverage | Adequate insurance coverage? Risk of contraction of certain conditions (currently: TSE, CJD, Hepatitis Non A, HIV, AIDS, ARC and similar syndrome/condition). | No insurance cover for claims relating to certain conditions (currently: TSE, CJD, Hepatitis Non A, HIV, AIDS, ARC and similar syndrome/condition). |  |  |  | #N/A | [] Notify Insurance Services and UQ Office of Research Ethics as early as possible prior to commitment to trial involving these conditions – Insurance Services to engage insurer to explore whether or not insurance cover can be obtained despite exclusion [] Consider appropriate controls where enrolling participants with these conditions in other trials [] Add other proposed controls for implementation |  |  |  |  | #N/A
Foreign Jurisdiction Requirements | Trial is conducted interstate of overseas? | Risk exposures to the University due to inability to manage foreign jurisdictions requirements resulting in severe consequences (prosecution, reprimand or jail), reputational damage and significant financial losses. |  |  |  | #N/A | [] Identify site requirements including relevant legal/regulatory requirements. UQ's Office of Research Ethics can assist with obtaining confirmation from UQ Legal Services of the overseas requirements [] Establish oversight responsibility at each site [] Establish coordination of site responsibilities [] Ensure that measures are in place to fully meet compliance obligations and appropriate insurance coverage [] Obtain RPM and Research Legal review of all contracts [] Add other proposed controls for implementation |  |  |  |  | #N/A
Quarantine Regulations | Will there be an Import/Export of biological material? | Inability to demonstrate compliance with Quarantine regulations resulting in project delays and/or financial losses. |  |  |  | #N/A | [] Manage transport/import/export requirements in accordance with relevant quarantine regulations [] Add other proposed controls for implementation |  |  |  |  | #N/A
Conflict of Interest | Potential conflict of interest, perceived and actual conflict, e.g. ° personal financial gain from the use of UQ research (directly or indirectly via family relationship and/or having interest in related research party), or ° providing outside organisations access to UQ IP without following UQ policy and procedures | Risk of losing credibility and reputation due to undeclared or unmanaged conflict of interest, including commercialisation and financial conflicts of interest |  |  |  | #N/A | [] CI and senior CT staff to assess and disclose conflicts of interest, with COI management plans developed, reviewed and approved |  |  |  |  | #N/A
| ADD other identified risks not included above | Risk of (describe risk event), due to (describe vulnerability / threats) resulting in (describe impact) | Add existing controls that may be unique to your activity |  |  | #N/A | [] Add other proposed controls for implementation |  |  |  |  | #N/A
4. Facilities, Equipment and Resources (including staff)
Project Resourcing | Appropriate resources and facilities to successful conduct the trial, e.g. ° Fit for purpose facility ° Equipment is available ° Data storage is appropriate ° Data collection and transfer ° Secured Medication cabinet available ° Staffing appropriate ° Data storage is appropriate ° Emergency Management Plan exists ° Manufacturing contracts established ° Sample Management / Logistics understood | Inability to successfully delivery the project milestones/outcomes due to inadequate project management and resourcing (e.g. staffing, facilities, equipment, ITS management, data management, operational support) |  |  |  | #N/A | [] Ensure adequate and sufficient clinical area and clinical equipment [] Make available resuscitation equipment [] Presence of trained personnel who can respond to emergencies [] Ensure proper maintenance and monitor adequate working of equipment: - Cold storage, refrigeration and freezer - Implement back-up strategy in case of power loss - medication storage is lockable and access log is available [] Secure laboratory space [] Establish and monitor data quality control [] Provide and monitor medication procedure [] Ensure appropriate packaging and distribution of medication and bio specimens established and monitored [] Organise postal / shipping logistics [] Process unused medication [] Ensure appropriate staff are recruited to complete task []Maintain adequate resourcing including consideration of - provision of leave - recruitment procedures - EBA [] Add other proposed controls for implementation |  |  |  |  | #N/A
Research Staff | Has all key personnel employment established? Staff training and credentialing is appropriate Delegation Log implemented GCP certification updated | Project is highly dependent on a research staff to successfully deliver project outcomes |  |  |  | #N/A | [] Project plan identifies a group of researchers including PhD students who already have a high understanding and skills required to continue with the research in case of key staff member departure/inability to complete the project [] Where the key research staff is not in a continuing position, check to ensure that they have been appointed for the duration of the contract period at a minimum [] Provide GCP training and investigator training [] Establish a delegation log and ensure staff are aware of their responsibilities [] Succession planning and/or cross skilling of staff to provide back up for key project staff ensuring project continuity [] Add other proposed controls for implementation |  |  |  |  | #N/A
5. Financial
Funding Obligations | Is there sufficient funding to complete the trial, e.g. ° Funding is appropriate ° Payment by contractual terms ° Payment by recruitment ° Payment by milestones ° Grant only | Risk of breaching funding/contract obligations resulting in loss of income and negative reputational outcomes |  |  |  | #N/A | [] Develop a comprehensive budget for the trial project including costs related to e.g. staff, facilities, equipment (purchase and maintenance), travel (transport, accommodation), disposable items, ITS/computers/data storage [] Ongoing budget monitoring against actual costs, project progress, key deliverables and obligations together with your Management Accountant [] Add other proposed controls for implementation |  |  |  |  | #N/A
Funding Variations | Has there been variations in the original funding/contractual agreement? | Risk of loss of income and/or unforeseen costs due to changes in protocol, or funding conditions material in nature resulting in financial loss |  |  |  | #N/A | [] Where the budget change is material in nature, a formal variation is submitted to the funding agency [] Work together with the Management Accountant and or UQR&I for ongoing budget monitoring against actual costs, project progress, key deliverables and obligations [] Add other proposed controls for implementation |  |  |  |  | #N/A
| ADD other identified risks not included above | Risk of (describe risk event), due to (describe vulnerability / threats) resulting in (describe impact) | Add existing controls that may be unique to your activity |  |  | #N/A | [] Add other proposed controls for implementation |  |  |  |  | #N/A
6. Pharmacovigilance and Safety Reporting
Pharmacovigilance and Safety Reporting | Safety is managed: Monitoring Plan Management of Safety events Data Safety Management Board or safety committee | Risk of participant harm due to lack of monitoring or incomplete information with respect to medicine safety profile resulting in trial cessation |  |  |  | #N/A | [] Outline how safety events will be identified [] State time period for collecting safety events [] Establish how safety events are to be reported [] Establish responsibilities for reporting safety events [] Add other proposed controls for implementation |  |  |  |  | #N/A
| ADD other identified risks not included above | Risk of (describe risk event), due to (describe vulnerability / threats) resulting in (describe impact) | Add existing controls that may be unique to your activity |  |  | #N/A | [] Add other proposed controls for implementation |  |  |  |  | #N/A
7. Investigational Medicine / Device
Investigational Medicine / Device | Medication Risk Standard Medical Care Drug on ARTG but for new purpose/dosage New Restriction on use Route of administration | Risk of participant harm due to safety profile of medication not being understood resulting in cessation of trial. |  |  |  | #N/A | [] Understand safety profile of compound [] Explain existing drug interactions [] Determine risks associated with 1- Study phase 2- Interactions with concomitant / permitted medications 3- Fertility, reproduction and pregnant women 4-Vulnerable participants [] Provide appropriate medication storage [] Ensure procurement of all necessary compounds including placebo [] Ensure drug/device security, storage and supply logistics are managed [] Seek relevant Good Manufacturing Practice (GMP) requirements [] Ensure medication/device labelling comply with regulatory requirements [] Consider medication expiry dates and re-supply requirements [] Receive updates and alerts of any changes to the product information/safety profile [] Add other proposed controls for implementation |  |  |  |  | #N/A
| ADD other identified risks not included above | Risk of (describe risk event), due to (describe vulnerability / threats) resulting in (describe impact) | Add existing controls that may be unique to your activity |  |  | #N/A | [] Add other proposed controls for implementation |  |  |  |  | #N/A
8. Procedures or Investigations
Procedures or Investigations | Procedures are managed: Blood Sampling Biopsy Radiation | Risk of participant harm, poor resource utilisation and/or additional costs being incurred. |  |  |  | #N/A | [] Ensure staff appropriately qualified / competent [] Screen participants [] Maintain Local Standard Operating Procedures (LSOPs) [] Calibrate according to LSOPs [] Obtain Medical Physicist report [] Perform an interim review of data to ensure that it is accurate and the LSOPs are being followed, samples/scans are suitable, etc. [] Add other proposed controls for implementation |  |  |  |  | #N/A
| ADD other identified risks not included above | Risk of (describe risk event), due to (describe vulnerability / threats) resulting in (describe impact) | Add existing controls that may be unique to your activity |  |  | #N/A | [] Add other proposed controls for implementation |  |  |  |  | #N/A
9. Health Intervention
Health Intervention | Procedures are managed: List interventions and scales | Risk of participant harm or withdrawal due to intervention resulting in additional recruitment (delay) or cessation of trial. |  |  |  | #N/A | [] Ensure staff appropriately qualified / competent [] Screen participants [] Maintain Local Standard Operating Procedures (LSOPs) [] Calibrate according to LSOPs [] Obtain Medical Physicist report if required [] Add other proposed controls for implementation |  |  |  |  | #N/A
| CT participant with potential and/or incidental medical condition? | CT participant presenting with potential medical condition outside of the expertise of the CT clinician – facilitating appropriate treatment |  |  |  | #N/A | [] Referral to colleague in relevant discipline and/or referral to GP; follow up at subsequent meetings regarding condition |  |  |  |  | #N/A
| ADD other identified risks not included above | Risk of (describe risk event), due to (describe vulnerability / threats) resulting in (describe impact) | Add existing controls that may be unique to your activity |  |  | #N/A | [] Add other proposed controls for implementation |  |  |  |  | #N/A
10. Observation / Educational
Observation / Educational | Procedures are managed: List requirements or program items and scales | Risk of participant harm or withdrawal due to participation resulting in additional recruitment (delay) or cessation of trial. |  |  |  | #N/A | [] Ensure staff appropriately qualified / competent [] Screen participants [] Maintain Local Standard Operating Procedures (LSOPs) [] Calibrate according to LSOPs [] Add other proposed controls for implementation |  |  |  |  | #N/A
| ADD other identified risks not included above | Risk of (describe risk event), due to (describe vulnerability / threats) resulting in (describe impact) | Add existing controls that may be unique to your activity |  |  | #N/A | [] Add other proposed controls for implementation |  |  |  |  | #N/A
11. General Health, Safety and Security
Health and Safety | Potentially hazardous environments e.g. temperature hazards, chemicals, radiation, biosecurity, limited sanitation and/or other personal hazards | Risk of personal harm due to staff exposure to hazardous environments, which could result in severe negative health impacts and reportable incidents. | [] Completed a risk assessment and management plan (UQSafe-Risk system) |  |  | #N/A | [] Conduct site safety assessment (including site visit). Where required, obtain the assistance of your relevant Work Health and Safety Coordinator (WHSC) [] Ensure that staff meets health verification requirements, i.e. vaccination and immunisation [] Establish Local Standard Operating Procedures [] Ensure that staff are familiar with site/facility specific policies and procedures [] Establish which OHS training and induction(s) are relevant and check that staff have completed this training and induction program prior to participation [] Determine license requirements and confirm that staff hold appropriate licenses [] Implement monitoring processes to ensure safety management procedures are implemented as intended and continue to be effective [] Add other proposed controls for implementation |  |  |  |  | #N/A
Health and Safety, Personal Security | UQ staff working overseas | - Health and safety risk to staff due to different environment, culture and values (e.g. LGBQTI acceptance), different threats (physical environment, transport/road safety), standards of acceptable behaviour, institutions’ governance and local regulations (e.g. safety of laboratories, hospitals) - Risk to staff personal security due to lack of awareness of local laws, appreciation of cultural sensitivities and knowledge about the physical environment (high security risk areas/suburbs). |  |  |  | #N/A | [] Staff to inform themselves via DFAT Smarttraveller country specific advice; https://www.smartraveller.gov.au/ [] UQ’s travel risk assessment process and approvals []Use of International SOS (ISOS) for pre-trip departure information and emergency response during travel (ISOS has an office in China that can provide assistance to UQ staff) [] Staff to attend UQ Travel/ISOS information/training sessions [] Visiting overseas facilities to physically inspect operations, facilities and activities ensuring compliance with contract terms and conditions, agreed risk management plan and ongoing wellbeing of students and staff. [] Legal liability and professional indemnity insurance coverage of staff working in foreign jurisdictions to be confirmed (contact Insurance Services) [] Add other proposed controls for implementation |  |  |  |  | #N/A
Queensland Workers Compensation | UQ staff working interstate or overseas (not relevant for short visits related to for example conference attendance or local presentations). | Staff not covered by workers compensation due to working interstate or overseas |  |  |  | #N/A | [] Ensure adequate workers compensation insurance, with the assistance of Work Injury Management (WIM) within UQ's Occupational Health & Safety Unit and/or Insurance Services |  |  |  |  | #N/A
| ADD other identified risks not included above | Risk of (describe risk event), due to (describe vulnerability / threats) resulting in (describe impact) | Add existing controls that may be unique to your activity |  |  | #N/A | [] Add other proposed controls for implementation |  |  |  |  | #N/A
12. Other
Other | Are there any other risks specific to your clinical trials? | Risk of (describe risk event), due to (describe vulnerability / threats) resulting in (describe impact) | Add existing controls that may be unique to your activity |  |  | #N/A | [] Add other proposed controls for implementation |  |  |  |  | #N/A
Definitions, Terms, Acronyms |  | RPM = Research Partnership Manager | GCP = Good Clinical Practice | SOP = Standard Operating Procedures |  |  | Helpful Contacts: https://research.uq.edu.au/contact | research.governance@research.uq.edu.au |  | to discuss UQ as sponsor of clinical trials.
|  | OSR = Office of Sponsored Research | TGA = Therapeutic Goods Administration | LS = Local Site |  |  | UQ Legal Services (Research): legal.admin@research.uq.edu.au | Enterprise Risk: https://governance-risk.uq.edu.au/functions-and-services/enterprise-risk
|  | CGA = Contract & Grants Accounting | WHO = World Health Organisation | SIV - Site Initiation Visit |  |  | Insurance Services: insurance@uq.edu.au | Office of Sponsored Research: https://research.uq.edu.au/office-sponsored-research
|  | HREC = Human Research Ethics Committee | ARTG = Australia Register of Therapeutic Goods | IMV = Interim Monitoring Visit |  |  | Contract & Grants Accounting: contractandgrants@uq.edu.au

## Risk Matrix
Enterprise Risk Matrix
| Insignificant (1) | Minor (2) | Moderate (3) | Major (4) | Critical (5)
| 1 | 2 | 3 | 4 | 5
Very High (5) | Medium | Medium | High | Extreme | Extreme
High (4) | Low | Medium | High | High | Extreme
Medium (3) | Low | Low | Medium | High | Extreme
Low (2) | Low | Low | Medium | Medium | High
Very Low (1) | Low | Low | Low | Medium | High